## Sheet1
BUG_ID | Module | Bug Description | Test Type | Severity | Developers Status | ReTest Bugs Status
BUG_01 | New Member Loan | When we start entering the phone number the validation display Please enter must be of 11 digits. It should be like Contact Number should consists of 11 digits. | Functionality Issue | Medium | done | done
BUG_02 | New Member Loan | When we enter the phone number less than 11 number then validation comes and then if we type one alphabet then validation fades out. | Functionality Issue | Medium | done | done
BUG_03 | New Member Loan | No validation applied in Guardian Phone Number. | Functionality Issue | Medium | done | done
BUG_04 | New Member Loan | Nationality Field is sticked to the Guardian Nationality. | UI Issue | Low | done | done
BUG_05 | New Member Loan | When we go to Online Saving Account Tab then we can type alphabets and special characters in Saving Amount Field. | Functionality Issue | Medium | done | done
BUG_06 | New Member Loan | In the Item Loan Tab, Invalid Date is showing -> 1. Select the date release 2. and then select the mode of payment 3. Cancel the date release 4. Then Invalid Date shows. | Functionality Issue | Medium | done | done
BUG_07 | New Member Loan | In the Item Loan Tab, We have fill the money in amortization but terms and Total is not coming. ( This Issue comes in same above scenario) | Functionality Issue | Medium | done | done
BUG_08 | New Member Loan | Suppose we have fill the data in the cash loan Tab and then after that when we change the Tabs then data gets removed from cash loan tab and vice versa. | Functionality Issue | Medium | it's not a issue | done
BUG_09 | New Member Loan | When we change the Item amount then terms are not changing. | Functionality Issue | Medium | done | done
BUG_10 | Multi Account Module | Remove the UnNecessary Spaces in customer name field. | Functionality Issue | Medium | done | done
BUG_11 | Multi Account Module | In the Cash Loan Tab, when we Select the terms automatically maturity date is being selected without selecting the Date release. | Functionality Issue | Medium | no issue | done
BUG_12 | Multi Account Module | In the Cash Loan Tab, When we select the date release after selecting the date release when we cancel the date release then in Maturity Date it shows Invalid Date. | Functionality Issue | Medium | done | done
BUG_13 | Multi Account Module | In the Item Loan Tab, Ammortization money calculation is wrong. Ammortization is calculated on the basis of Item amount not the Total amount. | Functionality Issue | Medium | done | done
BUG_14 | Multi Account Module | In the Item Loan Tab, Ammortization money calculation is wrong. Ammortization is calculated on the basis of Item amount not the Total amount. | Functionality Issue | Medium | done | done
BUG_15 | Multi Account Module | In the Item Loan Tab, When we change the Item Amount them amortization does not change because the terms are showing but amoertization is not changing. | Functionality Issue | Medium | done | done
BUG_16 | Emergency Loan | When we fill the customer ID, then in customer name suggestion undefined is coming. | Functionality Issue | Medium | done | done
BUG_17 | Emergency Loan | Correct the UI in which the columns are displaying. | UI Issue | Low | done | done
BUG_18 | Emergency Loan | In the Loan ID NAN is showing. | UI Issue | Low | done | done
BUG_19 | Emergency Loan | In the Cash Loan Tab, when we Select the terms automatically maturity date is being selected without selecting the Date release. | Functionality Issue | Medium | done | done
BUG_20 | Emergency Loan | In the Cash Loan Tab, When we select the date release after selecting the date release when we cancel the date release then in Maturity Date it shows Invalid Date. | Functionality Issue | Medium | done | done
BUG_21 | Emergency Loan | First Letter should be capital of save Text of save button. | UI Issue | Low | done | done
BUG_22 | Emergency Loan | In the Item Loan Tab, When we change the Item Amount them amortization does not change because the terms are showing but amoertization is not changing. | Functionality Issue | Medium | done | done
BUG_23 | Emergency Loan | In the Item Loan Tab, Ammortization money calculation is wrong. Ammortization is calculated on the basis of Item amount not the Total amount. | Functionality Issue | Medium | done | done
BUG_24 | Emergency Loan | Correct the UI of Ammortization field. | UI Issue | Low | done | discuss with areeb | RC
BUG_25 | Member Reloan | When we fill the Loan ID, then no data shows and in customer name undefined is coming. | Functionality Issue | Medium | done | done
BUG_26 | Member Reloan | When we fill the Loan ID, then no data shows and in customer name undefined is coming. | Functionality Issue | Medium | done | done
BUG_27 | Member Reloan | We have filled the loan ID after clicking on view ledger it is still showing me warning please fill loan ID. | Functionality Issue | Medium | if u entered paid loan id then it will work | done
BUG_28 | Member Reloan | In the Cash Loan Tab, when we Select the terms automatically maturity date is being selected without selecting the Date release. | Functionality Issue | Medium | no issue | done
BUG_29 | Member Reloan | In the Cash Loan Tab, When we select the date release after selecting the date release when we cancel the date release then in Maturity Date it shows Invalid Date. | Functionality Issue | Medium | done | done
BUG_30 | Member Reloan | First Letter should be capital of save Text of save button. | UI Issue | Low | done | done
BUG_31 | Member Reloan | In the Item Loan Tab, When we change the Item Amount them amortization does not change because the terms are showing but amoertization is not changing. | Functionality Issue | Medium | done | done
BUG_32 | Member Reloan | In the Item Loan Tab, Ammortization money calculation is wrong. Ammortization is calculated on the basis of Item amount not the Total amount. | Functionality Issue | Medium | done | done
BUG_33 | Member Reloan | When we fill customer ID then suggestion pop up list of customers is not displayed. When we fill first time and click it works but when we again fill then it doesnot work. | Functionality Issue | Medium | done | done
BUG_34 | Ovedue Reloan | LIST OF CUSTOMER OVERDUE ACCOUNT list is not displaying as NPL 202 loan ID has a overdue amount. | Functionality Issue | Medium | done | done
BUG_35 | Ovedue Reloan | In the Item Loan Tab, When we change the Item Amount them amortization does not change because the terms are showing but amoertization is not changing. | Functionality Issue | Medium | done | done
BUG_36 | Overdue Reloan | In the Item Loan Tab, Ammortization money calculation is wrong. Ammortization is calculated on the basis of Item amount not the Total amount. | Functionality Issue | Medium | done | done
BUG_37 | Overdue Reloan | In the Cash Loan Tab, When we select the date release after selecting the date release when we cancel the date release then in Maturity Date it shows Invalid Date. | Functionality Issue | Medium | done | done
BUG_38 | Add Branch | Contact No and other Contact Number field is supporting less than 11 value number. | Functionality Issue | Medium | done | done
BUG_39 | Add Branch | If Branch already exists, then wrong message it is displaying. It should be Branch already exists not branch already exit. | Functionality Issue | Medium | done | done
BUG_40 | Add Area | If Area already exists, then wrong message it is displaying. It should be Area already exists not area already exit. | Functionality Issue | Medium | done | done
BUG_41 | Add Area | If Area already exists, then wrong message it is displaying. It should be Area already exists not area already exit. | Functionality Issue | Medium | done | done
BUG_42 | Field Payment | Correct the UI of other accounts sections columns. | UI Issue | Low | done | done
BUG_43 | Field Payment | Correct the UI of other payment details columns. | UI Issue | Low | done | done
BUG_44 | Field Payment | When we start typing Loan ID then in suggestion pop box, all the fileds of columns are overlapping with each other. | Functionality Issue | Medium | done | discuss with areeb | RC
BUG_45 | Field Payment | When we hover onto the clear total and total button then there should be different color not black. | UI Issue | Low | done | total button is ok work on clear total also | RC
BUG_46 | Customer List | When we click on the View Button then Good Payer and Bad Payer Button UI is not correct. | UI Issue | Low | done | done
BUG_47 | Customer List | When we click on the Good Payer and Bad Payer Button then nothing is happening. | Functionality Issue | Medium | done | done
BUG_48 | Customer List | When we hover onto the View Text ..text not seeing. | UI Issue | Low | done | done
BUG_49 | Customer List | When we click on the view button and then after clicking on cancel loan field whether status is active or inactive , same message is displaying Do you want to cancel this loan? | UI Issue | Low | done | done
BUG_50 | Collection of Charges Reports | When we select the Branch and Area and then after that clicking on the submit button the data does not come. | Functionality Issue | Medium | done | done
BUG_51 | Collection of Charges Reports | When we select all fields and then after cancelling the start and end date and then after we click on submit button then error comes in console cannot rrad properties of null. | Functionality Issue | Medium | done | done
BUG_52 | Collection of Charges Reports | Without Selecting anything and then after clicking on the submit button total field is displaying an amount. | Functionality Issue | Medium | done | done
BUG_53 | New and Renewed Loans | When we enter Branch and date and click on the submit button then in column of hand over by it is displaying undefined between first and last name. ( Refer to screenshot) | UI Issue | Low | done | done
BUG_54 | New and Renewed Loans | When we enter Branch and date and click on the submit button then in column of hand over by it is displaying undefined between first and last name. ( Refer to screenshot) | UI Issue | Low | done | done
BUG_55 | New and Renewed Loans | Suppose we havent fill any date and click on submit button and after that in date text Invalid date is displaying. ( Refer to screenshot) | Functionality Issue | Medium | working from my side | done
BUG_56 | Withdraw | Customer ID label is attached to the NPC dropdown. ( Refer to Screenshot ) | UI Issue | Low | client requirement | done
BUG_57 | Withdraw | I have a savings amount 0 but still the current balance is increasing why?? ( Refer to Screenshot ) | Functionality Issue | Medium | done | done
BUG_58 | Item Return Deposit | Complete Placeholder is not displaying Please enter Loan ID. | Functionality Issue | Medium | done | done
BUG_59 | View Assign Task | Without selecting the branch, area and collector and then after click on the search button all data displays. | Functionality Issue | Medium | done | done
BUG_60 | View Assign Task | When we select the branch and area after clicking on search no search related data comes. | Functionality Issue | Medium | DONE | done
BUG_61 | View Assign Task | Collectors are not displaying in dropdown. | Functionality Issue | Medium | DONE | done
BUG_62 | Daily Collection | UI is not impressive of Daily Collection ( Refer to Screenshot ) | UI Issue | Low | client requirement | done
BUG_63 | Collector Details | When we want to see the view the details and click on the view button some details are not displaying ( Refer to Screenshot ) | UI Issue | Low | on hold
BUG_64 | Customer Info | Enter customer ID spelling is wrong. | UI Issue | Low | done | done
BUG_65 | Customer Info | First Letter should be capital of Enter Customer ID | UI Issue | Low | done | done
BUG_66 | Customer Info | After filling the customer Id when we cancel the customer ID then in height field undefined undefined comes ( Refer to ScreenShots ) | Functionality Issue | Medium | done | done
BUG_67 | Add User -> Add Staff | If we try to add the same user then it shows me warning email already registered. The spelling of registered is wrong. | UI Issue | Low | done | Not Done Yet
BUG_68 | Add User -> Edit Staff | When we search the user it is showing me gurinder undefined singh | Functionality Issue | Medium | done | done
BUG_69 | Add User -> Edit Staff | When we click on the update user without modifying any data it is showing me this messagePlease enter the contact number of service user Please enter 11 digits for phone number ( Refer to Screenshot ) | UI Issue | Low | done | Not Done Yet
BUG_70 | Add User -> Edit Staff | Update User is not working. | Functionality Issue | Medium | done | Done
BUG_71 | Add User -> Edit Staff | Update User is not working. | Functionality Issue | Medium | done | Done
BUG_72 | Add User -> Edit Staff | When we update the user the previous user data which we have added does not display in the search field. | Functionality Issue | Medium | done | Done
BUG_73 | Add User -> Delete Staff | In the Delete Staff List, in the username field undefined is coming. | UI Issue | Low | done | done
BUG_74 | Edit Loan | When we try to change the amount release then in other fileds nothing is happening. It should change when release amount gets changed. ( Refer to Screenshot ) | Functionality Issue | Medium | done | Done
BUG_75 | Edit Savings | When we try to add the withdraw savings greater than deposit savings then message should come as Withdraw Savings should not be greater than deposit savings . | Functionality Issue | Medium | done | Done
BUG_76 | Edit Savings | When we try to add the withdraw savings greater than deposit amount and after clicking on update button it is giving me success message | Functionality Issue | Medium | done | Done
BUG_77 | Edit Savings | When we try to hover onto the update button then update text does not display. | UI Issue | Low | done | done
BUG_78 | Edit Customer Info | When I try to update the user then it is giving me message please fill all the details. Details are already filled why it is giving me validation? | Functionality Issue | Medium | done | done
BUG_79 | Edit Branch and Area | Contact No and other Contact Number field is supporting less than 11 value number. | Functionality Issue | Medium | done | done
BUG_80 | Edit Branch and Area | First Letter should be capital of updated branch successfully. | UI Issue | Low | done | done
BUG_81 | Edit Branch and Area | When I do not fill anything in the area then something went wrong message is displaying. | Functionality Issue | Medium | done | done
BUG_82 | Delete Customer | Customer ID label is attached to the NPC dropdown. | UI Issue | Low | no issue | done
BUG_83 | Delete Customer | When we do not fill the complete customer ID, then in name field undefined is coming. | Functionality Issue | Medium | done | done
BUG_84 | Delete Customer | When we click on the delete button the UI of pop up box is not good...submit button go outside of the box. | UI Issue | Low | done | done
BUG_85 | Delete Loan ID | Loan ID label is attached to the NPC dropdown. | UI Issue | Low | correct | done
BUG_86 | Add/ Delete Collector | When we click on the save button without fill any detail the Loading... in save button does not stop. It is continuously resuming. | UI Issue | Low | done | done
BUG_87 | Add/ Delete Collector | When we select the contract start date and then cancel the contract start date after cancelling in contract end date Invalid date display | Functionality Issue | Medium | done | done
BUG_88 | Add/ Delete Collector | If user already exists then no validation message is coming. ( Refer to Screenshot ) | Functionality Issue | Medium | done | done
BUG_89 | Add/ Delete Collector | Add Collector is not working. Error is displaying in Network Tab. StaffUser validation failed: invitedRole: Path `invitedRole` is required . ( Refer to Screenshot ) | Functionality Issue | Medium | done | done
BUG_90 | Edit Collector | Success message display in network 200 status coming but nothing is happening in UI. . ( Refer to Screenshot ) | Functionality Issue | Medium | done | done
BUG_91 | List Bad Payer Customer | Good Payer Customer is not showing in the list. | Functionality Issue | Medium | done
BUG_92 | List Good Payer Customer | Good Payer Customer is not showing in the list. | Functionality Issue | Medium | done
BUG_93 | List InActive Cutomer | List of Inactive Customers are not displaying. ( I have marked the person as Inactive Customer ) | Functionality Issue | Medium
BUG_94 | Add Latest Banner | Updating the product is not working It is not giving me any message in UI we have to refresh then changes gets updated. | Functionality Issue | Medium | done | done
BUG_95 | Mobile Leads | When we hover onto the Action Column Icons , the icons are not visible. | UI Issue | Low | done
BUG_96 | Mobile Leads | All the Fields of Data is sticked to the border of the Table. | UI Issue | Low | done
BUG_97 | Mobile Leads | When I clicked on the Delete Icon. Things Need to Correct 1. When we hover onto the submit button the text is not seeing properly. 2. Submit button is not working. 3. Closing the Pop Up Box is not working. | Functionality Issue | Medium | done
BUG_98 | Customer Information Form | When I click on the submit button without fill anything no validations are coming in UI. No validations applied. | Functionality Issue | Medium | done | done
BUG_99 | List of Customer Per Area | In customer ID NAN is displaying. | Functionality Issue | Medium | done | done
BUG_100 | Upload Excel Sheets | No Validation is coming without filling any data when I click on the save button of Upload Excel Sheets | Functionality Issue | Medium | done | done
BUG_101 | Upload Excel Sheets | When I select the file from computer then loader continously move and I cannot able to click on the save button. | Functionality Issue | Medium | done | Not Done Yet
BUG_102 | RDB Reloan | When we try to type alphabets in the New Loan amount , then in Receiving amount Nan is displaying. | Functionality Issue | Medium | done | done
BUG_103 | RDB Reloan | When we type new loan amount then receiving amount automatically comes but we able to edit the Receiving amount. | Functionality Issue | Medium | done | done
BUG_104 | RDB Reloan | No validations are coming in UI if we do not fill the complete details. It is coming in the Network Tab. | Functionality Issue | Medium | done | Not Done Yet
BUG_105 | New Staff Loan | No validations are coming in UI if we do not fill the complete details. It is coming in the Network Tab. | Functionality Issue | Medium | on hold
BUG_106 | New Staff Loan | Maturity Date field should be disabled when we select the Date release field. | Functionality Issue | Medium | on hold
BUG_107 | New Staff Loan | Amortization is calculated on the basis of Item amount not Total Amount. | Functionality Issue | Medium | on hold

## ScreenShots
BUG_07
BUG_08
BUG_11
BUG_12
BUG_13
BUG_14
BUG_15
BUG_16
BUG_20
BUG_48
BUG_49
BUG_50
BUG_51
BUG_52
BUG_57
BUG_58
BUG_61
BUG_65
BUG_69
BUG_83
BUG_84
BUG_85