## Sheet1
BUG_ID | Module | Bug Description | URL | Test Type | Developers Status | ReTest Bugs Status
BUG_01 | Login Module | When we Link our account with Email ID the no message shows Login Successful. |  | Functionality Issue | Done | Done
BUG_02 | Profile Module | If we want to remove the profile pic and we do not want to upload any profile pic there is no option available. |  | Functionality Issue | Done | Done
BUG_03 | Profile Module | If we want to remove the cover photo and we do not want to upload any cover photo there is no option available. |  | Functionality Issue | Done | Done
BUG_04 | Profile Module | When we click on the edit profile and after clicking on submit button then wrong message shows Contact Updated Successfully. |  | Functionality Issue | Done | Done
BUG_05 | Profile Module | Submit button of edit profile working when we click 2 Times. |  | Functionality Issue | Done | Done
BUG_06 | Profile Module | If we follow and unfollow any post, then there is no change shows in followers and following notification numbers.. |  | Functionality Issue | Done | Partially Done
BUG_07 | My Collections Module | There is no option available of edit and deleting the folder. |  | Functionality Issue | Done | Done
BUG_08 | My Earnings Module | When we click on the redeem coin button then no message display Crux level will open after Level 10. |  | Functionality Issue | Solve when crux level achieve level 10. ( Solve from back end) | Done
BUG_09 | My Earnings Module | When the coins are deducted from admin panel then negative Balance shows in Mobile App. |  | Functionality Issue | Done | Ask from Client ( Not Done Yet )
BUG_10 | My Earnings Module | When we click on the Last year dropdown field of statistics graph takes so much time to come. |  | Functionality Issue | Done | Done
BUG_11 | My Earnings Module | In My Last Week Summary, the no.s are not displaying in the total. |  | Functionality Issue | Done | Done
BUG_12 | Bounty Module | Invite a Friend button is not working. |  | Functionality Issue | Done | Done
BUG_13 | Settings Module -> Basic Info | When we click on the save button then message shows contact updated successfully. |  | Functionality Issue | Done | Done
BUG_14 | Settings Module -> Basic Info | When we update anything and click on the save button then update functionality is not working. |  | Functionality Issue | Done | Done
BUG_15 | Settings Module -> Account Settings | When we click on the save button then message shows contact updated successfully. |  | Functionality Issue | Done | Done
BUG_16 | Settings Module -> Account Settings | When we update anything and click on the save button then update functionality is not working. |  | Functionality Issue | Done | Done
BUG_17 | Settings Module -> Redeem Settings | When we update anything and click on the update button then update functionality is not working. |  | Functionality Issue | Solve Later On Requirement of Client
BUG_18 | Settings Module -> Notification Settings | Notification setting update successfully message ( Wrong Spelling of Setting). |  | UI Issue | Done | Done
BUG_19 | Notifications Module | Warnings, Spankees and your coins has been deducted they are showing undefined. |  | Functionality Issue | Solve from backend | Done
BUG_20 | Posts Module | When we publish any Post , the notification numbers are not updated. |  | Functionality Issue | Done | Done
BUG_21 | Posts Module | When we enter more than 10 posts then posts notification number goes in negative values. |  | Functionality Issue | Solve from backend | Not Done Yet
BUG_22 | Posts Module | When we delete post then notification number do not increase. |  | Functionality Issue | Done | Done
BUG_23 | Posts Module | We can report the user without selecting any item. |  | Functionality Issue | Done | Done
BUG_24 | Posts Module | No notification shows to another user when we follow the person. |  | Functionality Issue | Solve from backend | Not Done Yet
BUG_25 | Posts Module | When we like and comment the post of another user the notification do not show to another user. |  | Functionality Issue | Solve from backend | Not Done Yet
BUG_26 | Posts Module | Like and comment is working but we have to refresh 2 times to update the data to another end. |  | Functionality Issue | Solve from backend | Not Done Yet
BUG_27 | Posts Module | When we block any user from three dots then block user comes in the blocked user settings but when we unblock user from settings then user unblock from settings but after than when we check the three dots then it shows unblock user. |  | Functionality Issue | Solve from backend | Not Done Yet
BUG_28 | Posts Module | When we unfollow anyone posts do not remove of another user. |  | Functionality Issue | Solve from backend | Not Done Yet
BUG_29 | Search Module | If we want to search anything and want to go back then application close immediately. |  | Functionality Issue | Done | Done
BUG_30 | Search Module | Searching any keyword is not working. |  | Functionality Issue | Done | Done
BUG_31 | Search Module | If the search is not related to the application then it does not show anything no data found yet. |  | Functionality Issue | Done | Done
BUG_32 | Search Module | If we click on any Tag and then if we press back button then application close immediately. |  | Functionality Issue | Done | Done
BUG_33 | Top 10 Module | If we click any photo in Top 10 and after that if we pass comments without writing any comment and press send button then comments numbers continuously increasing and when again we see the comments then it shows the empty number comments |  | Functionality Issue | Done | Done
BUG_34 | Top 10 Module | The same comments are displaying in every post when we click on the top 10 images. |  | Functionality Issue | Done | Done
BUG_35 | Check Profile of other user. | Block and Unfollow Issue. |  | Functionality Issue | Solve from backend | Not Done yet