## Sheet1
BUG_ID | View | Page | Bug Description | URL | Test Type | Developers Status | Retest Bugs ( Tester )
BUG_01 | Mobiles ( Samsung Galaxy s8+) | Home Page | In the get in touch section, There should be some gap between pick up date and drop off date | https://swan-hill-taxi-cab.webflow.io/ | UI issue | Done | Done
BUG_02 | Mobiles ( Samsung Galaxy s8+) | Home Page | In the get in touch section, There is no equal gap between the fields | https://swan-hill-taxi-cab.webflow.io/ | UI issue | Done | Not Done Yet
BUG_03 | Mobiles ( Samsung Galaxy s8+) | About Us Page | In the Benefits you get section, icons and text aligment is not responsive | https://swan-hill-taxi-cab.webflow.io/about-us | UI issue | Done | Done
BUG_04 | Mobiles ( Samsung Galaxy s8+) | Services Page | In the Parcel Delivered Section, there should be some padding in the box. | https://swan-hill-taxi-cab.webflow.io/services | UI issue | Done | Done
BUG_05 | Mobiles ( Samsung Galaxy s8+) | Drivers Page | The Drivers spelling is wrong in navigation bar in mobile menu. | https://swan-hill-taxi-cab.webflow.io/how-to-become-a-driver | UI Issue | Done | Done
BUG_06 | Mobiles ( Samsung Galaxy s8+) | Drivers Page | Apply Now form fields alignment is not responsive. | https://swan-hill-taxi-cab.webflow.io/how-to-become-a-driver | UI Issue | Done | Done
BUG_07 | Mobiles ( Samsung Galaxy s8+) |  | When we open the nav link of drivers and transfers in mobile phone then link is opened in a new tab. |  | UI Issue | Done | Done
BUG_08 | Mobiles ( Samsung Galaxy s8+) | Contact Page | Contact Form is not responsive | https://swan-hill-taxi-cab.webflow.io/contact | UI Issue | Done | Not Done Yet
BUG_09 | Mobiles ( Samsung Galaxy s8+) | Contact Page | Give some Margin bottom to the map | https://swan-hill-taxi-cab.webflow.io/contact | UI Issue | Done | Not Done Yet
BUG_10 | Tablets ( IPad Air) | Home Page | In the Awesome Features Section, The boxes alignment is not right. | https://swan-hill-taxi-cab.webflow.io/ | UI Issue | Done | Done
BUG_11 | Tablets ( IPad Air) |  | When we open the nav link of drivers and transfers in Tablets then link is opened in a new tab. |  | UI Issue | Done | Done
BUG_12 | Tablets ( IPad Air) | Home Page | In the our Services Section, Read More Button is sticked to the box. | https://swan-hill-taxi-cab.webflow.io/ | UI Issue | Done | Done
BUG_13 | Desktops/Laptops ( Nest Hub Max ) | About Us Page | In the Benefits you get section, icons and text aligment is not responsive | https://swan-hill-taxi-cab.webflow.io/about-us | UI Issue | Done | Done
BUG_14 | Desktops/Laptops ( Nest Hub Max ) | Home Page | In our services Section boxes height is not equal. please check all the 3 boxes carefully. | https://swan-hill-taxi-cab.webflow.io/ | UI Issue | Done | Done
BUG_15 | Desktops/Laptops ( Nest Hub Max ) |  | Contact Page is not displaying in Desktops. | https://swan-hill-taxi-cab.webflow.io/ | UI Issue